## BUDGET
SUBJECT | SUPPLIER | PRICE | VAT | STATUS | COMMENTS | הערה אחרונה על ידי עדי | DEADLINE | PRICES WITHOUT VAT | PRICES WITH VAT | NOTES | Amount to be paid now- percentage | Amount to be paid now / Paid | Remaining amount to be paid | עבודה שנשארה | Account details | STATUS
Interior Design | Yael Siso | [6 empty] | 80000 | 94400 | 30% - Down payment. 20% - After concept and layout plan approval. 20% - After completing the working plans. 10% - During the supervision stage (at the start of construction work). 20% - Upon project completion (two weeks after moving in). | 90% | 84960 | 9440 |  |  | Partially paid 84960
Bill of Quantity | [7 empty] | 8500 | 10030 |  | 100% | 10030 | 0 |  | שם החשבון באנגלית KEIZMAN ASI AND KEIZMAN GONI IBAN : IL130121700000000392274 SWIFT : POALILIT | Fully paid 10030
Main contractor | TOMER |  |  | אושר |  |  |  | 750429.66 | 885506.9988 | • Advance payment before starting the works – 10% Amount before VAT: 61,609 NIS. VAT (18%): 11,089 NIS Total payment: 72,698 NIS • Upon completion of demolition works – 10% Amount before VAT: 61,609 NIS VAT (18%): 11,089 NIS Total payment: 72,698 NIS • Upon completion of electrical infrastructure works – 10% Amount before VAT: 61,609 NIS VAT (18%): 11,089 NIS. Total payment: 72,698 NIS • Upon completion of plumbing works – 10% Amount before VAT: 61,609 NIS. VAT (18%): 11,089 NIS Total payment: 72,698 NIS • Upon completion of ceiling construction (before closing with gypsum) – 20% Amount before VAT: 123,218 NIS. VAT (18%): 22,179 NIS Total payment: 145,397 NIS • Upon completion of flooring and tiling works – 20% Amount before VAT: 123,218 NIS. VAT (18%): 22,179 NIS Total payment: 145,397 NIS • Upon completion of first coat of paint – 15% Amount before VAT: 92,414 NIS. VAT (18%): 16,635 NIS Total payment: 109,049 NIS • Two weeks after handover – 5% Amount before VAT: 30,805 NIS. VAT (18%): 5,545 NIS Total payment: 36,350 NIS |  | 784042.12 | 68164.8788 |  |  | Partially paid 145,396, Partially paid 312,140.68, Partially paid 200,000, Partially paid 67,505.44, Paritally paid 59000
Parquet Flooring | HEZI BANK | [6 empty] | 47026.08 | 55490.7744 |  |  | 138067 | -0.4126 |  |  | Partially paid 42000, Partially paid 48048, Partially paid 48019 Fully Paid-138,068
Sanitary ware, cladding and flooring |  | 78374 | included | אושר ושולם | המחיר לא סופי, כיור עומד? | כיור שירותי אורחים לסגור +ללכת לראות במודי 120/120 עובי 2 ס"מ |  | 69980.35 | 82576.813 | 120/120 cm Replace the shower head with a ceiling-mounted one; verify the exact number of tiles. | 100% |  |  |  | Bank: BANK LEUMI LE ISRAEL B.M. Main Branch: Tel Aviv (No. 800) Address: Herzl 19 Account No.: 828223/82 Account Name: HEZIBANK DESIGN LTD SWIFT Code: LUMIILITXXX IBAN: IL18 0108 0000 0008 2822 382
Microtoping- Outdoor Flooring |  | 540 for skm אם מבצעים מיקרוטופינג על ריצוף סוג ב | [6 empty] | 0 |  |  |  | 0 |  |  | Partially paid 42000
Microtoping- cladding | MIKI ESHEL | 550 for skm | [6 empty] | 0 |  |  |  | 0 |  |  | Partially paid 42000
A.C. | ADIR |  | not included | אושר |  | לעבור עם בני בשטח עם התכנית לוודא שהכל מובן שלא חסר כלום. בעיקרון כבר עשינו את זה. אבל רק לוודא לפני ביצוע. לתאם איתו את הפתח גישה ליחידה בקיר קמין |  | 77000 | 90860 | For replacing the air conditioning units in the bedrooms — each room will get a separate unit. The work includes: ❖ A concealed unit for the master bedroom that will cool both the bedroom and the safe room (Mamad) ❖ 2 units for the kids’ rooms ❖ Replacing all grills in the apartment ❖ Relocating and modifying the living room A/C unit, including replacing the shutters there too Preliminary price offer – ₪55,000 + ₪16,000 for replacing the central air-conditioning unit + ₪6,000 for 4 new sound-insulated fans. Total: ₪77,000 before VAT. | 100% | 90860 | 0 |  | BANK DETAILS Bank name: Mizrahi-Tefahot Bank Account number: 425-499645 IBAN: IL59-0204-2500-0000-0499-645 SWIFT code: MIZBILITXXX | Fully Paid- 90860
Lighthing | GUY MISHALY | [6 empty] | 1440 | 1699.2 | decorative lighting for guest toilet | 100% | 1699.2 | 0 |  | Bank- Mizrahi Tfahot Branch- 441 Account Name- Rachel Osnat Boxnboim Guy Michaly Account Address- Hanevi’im 26, Haifa, 3310405 IBAN- IL780204410000000209615 SWIFT- MIZBILIT | Fully paid 1699
| YAIR DORAM | 86000 | included | שולמה מקדמה בגובה 50% 43,000 |  | דוגמה של פס מגנטי לדימור להעביר לבן ויטראה- חיים הבטיח עד יום רביעי לפני הזמנה לביצוע לעבור עם חיים לוודא אורכים של כל הפסים, להבין מז'אן מארק למתי צריך את האספקה של הגופים. |  | 30463.5568 | 35946.997 | All lighting of the appartement excluding these: Table lamps in the kids’ rooms, concealed lighting and ceiling lighting for the balcony – to be checked in the plans. | 100% | 35946.997 | 0 |  | YAIR DORAM 1992 LTD Bank Hapoalim (12) Tel Aviv Branch (159) 23 Menahem Begin RD. Tel-Aviv Israel Account No. 128722 IBAN NO. IL87-0121-5900-0000-0128-722 Swift: POALILIT | Partially paid 17375, Partially paid 17375. Fully Paid-34750 + Paid 1197
Electricity | VITREA | 58355 | not included | שולמה מקדמה 30% + מעמ 20,657 ש"ח |  |  |  | 23791 | 28073.38 |  | 100% | 28073.38 | 0 |  | Vitréa is requesting full payment (since this is an order under ₪25,000). There is an option to pay by credit card, split into up to 4 installments, or by bank transfer for the full amount (they have an overseas bank account). Please let us know how you prefer to pay. If you choose credit card payment, we will pass your phone number to Vitréa and they will contact you to process the charge.BANK HAPOALIM B .M. BRANCH 584 SWIFT CODE: POALILIT IBAN NO: IL75-0125-8400-0000-0124-309 ACCOUNT NAME: VITREA SMART HOME TECHNOLOGIES LTD ACCOUNT NO: 124309 | Fully paid 28074
Switches | VITREA | [6 empty] | 748.305 | 882.9999 |  | 100% | 883 | -0.0001 |  |  | Fully paid 883
Audio Video | ARTZI | [6 empty] | 16160 | 19068.8 | Wi-Fi, camera, living-room TV, master-bedroom TV, preparations and installation | 100% | 19069 | -0.2 |  | Down payment 30% details: ARTZI ADVANCED COMMUNICATION SYSTEMS BANK HAPOALIM BRUNCH 640 ACCOUNT 133764 | Partially paid 4698, Partially paid 14371, Fully Paid-19,069
Carpentry + Kitchen |  | 368000 | included | אושר | 45K זיכוי אצל טולמנס | ברגע שמסיימים הכנות חשמל ואינסטלציה צריך להזמין את טולמנס לקחת מידות ולהוריד לביצוע, וממתינים לאישור פרביטל לחיזוקים באי |  | 187400 | 221132 |  |  | 165490 | 55642 |  | CARPENTRY RONY GABAY Bank 20 - MIZRAHI TEFAHOT BANK LTD Branch 511 - NES ZIONA IL620205110000000302943 MIZBILITXXX | Partially paid 65490
Electrical appliances | ELECTRIC PLUS |  | included | אושר ושולמה מקדמה |  |  |  | 28377.12 | 37412 | Option for a micro unit only, 38 cm height, hinged opening, at an additional cost : 2,100 NIS + VAT | 100% | 37412 | 0 |  | Account no.: 384200/39 Bank: Bank Leumi le Israel B.M. IBAN: IL50 0108 2700 0003 8420 039 Branch: Azur, 827 Address: 3 Herzl St. Azur, 58006 SWIFT: LUMIILITXXX | Paid (37412) 10000, Paid 27412 Fully Paid-138,068
Doors | SHAARY BRACHA | 79000 | included | אושר |  | לעקוב אחרי ז'אן מארק מתי אפשר להזמין אותם לקחת מידות ולהחליט לגבי הדלת שצמודה לטלויזיה |  | 36951 | 43602.18 |  | 100% | 43602.18 | 0 |  | Bank- Hapoalim Branch- 643 Account Name- SHAAREI BRACHA CARPENTRY LTD Account Address- HAMERKAVA 18 HOLON 5885409 IBAN- IL030126430000000444432 Swift- POALILIT | Partially paid 17441, Partially paid 26161, Fully paid 43602
MARBLE | MILSTONE - GRANIT PORCELANE | [6 empty] | 21589.83 | 25475.9994 | with stainless steel sink from hezibank | 100% | 25274.85 | 0 |  | מילסטו עיבודי שיש בע"מ בנק מזרחי סניף 416 חשבון 297573 | Partially paid 12744, Partially paid 12530.85 Fully paid 25275 | Bank- LEUMI Branch- 618 Account Name- Account Address- IBAN- IL400106180000000090021 Swift- LUMIILITXXX
Mirrors | A.A MIRRORS | [6 empty] | 8900 | 10502 | mirrors for guest toilet, kids bathrrom, master bathroom and mirror on the mamad door |  |  |  |  | AA MAROT LTD Bank name – MIZRAHI-TEFAHOT Routing No. – 495 Account No. – 180028 Swift – MIZBILITXXX Iban – IL87-0204-9500-0000-0180-028
Glass partitions | [7 empty] | 12000 | 14160 | This includes the seperation between the master bedroom and the master bathroom + the seperation between the master bathrrom and corridor.The master bathroom door is a standard hinged door | 36698
Glass Showers | [7 empty] | 10200 | 12036 | For kids bathroom and master bathroom shower
Total glasses & mirrors | [7 empty] | 31100 | 27730 |  | 100% | 27730 | 0 |  |  | Partially paid 18349, Partially paid 9381 Fully Paid- 27730
Countertops corian | BORISTONE | [6 empty] | 13984.7 | 16500 | This includes the countertop + sink of the kids and master bathroom cabinet | 100% | 16500 | 0 |  | BANK DETAILS Bank name – MIZRAHI-TEFAHOT Routing No. – 412 Account No. – 254357 Swift – MIZBILITXXX Iban – IL90-0204-1200-0000-0254-357 Beneficiary Name – OHAYOUN NAAMIT - BORISTONE | Partially paid 7450, Partially paid 9050 Fully Paid-16500
Curtains | YAIR | [6 empty] | 8759 | 10336 |  | 100% | 10336 | 0 |  | Bank name: Bank Hapoalim Bank code: 12 Branch number: 613 Account number: 79594 Account holder name: Gabrieli Yair IBAN: IL13 0126 1300 0000 079594 | Partially paid 5168, Partially paid 5168 Fully Paid-10336
Gardening | ITAY KIVITY | [6 empty] | 26600 | 31388 |  | 100% | 31388 | 0 |  | IBAN IL53-0127-4900-0000-0445-531 SWIFT POALILIT KVITY ITAI- GARDENING AND LANDSCAPING | Partially paid 9416, Partially paid 21972, Fully Paid-31388
Mamad Door | [7 empty] | 1500 | 1770 |  | 100% | 1770 | 0 |  |  | Fully paid 1770
Parquet installation | Whole wood | [6 empty] | 17609.58 | 20779.3044 |  | 86.62% | 20779 | 0.3044 |  |  | Partially paid 18000
Bench | Kuala | [6 empty] | 823.7288 | 972 |  | 100% | 973 | 0 |  |  | Fully paid 973
Water Filter | Gome | [6 empty] | 11237.3 | 13260.014 |  | 100% | 13260 | 0.014 |  |  | Fully paid 13260
Bathroom Accesories | Unico | [6 empty] | 1844.92 | 2177.0056 |  | 100% | 2177 | 0.0056 |  |  | Fully paid 2177
Cleaning | [7 empty] | 7200 | 8496 |  | 100% | 8496 | 0 |  |  | Fully paid 8496
Styling | [8 empty] | 0 |  |  |  | 0
Bedsheets, Cuttlery | [8 empty] | 0 |  |  |  | 0
Led for Bed | Yair Duram | [6 empty] | 779.66 | 919.9988 |  | 100% | 920 | -0.0012 |  |  | Fully paid 920
Art | [8 empty] | 0 |  |  |  | 0
Printing | C-Copy | [6 empty] | 931.36 | 1099.0048 |  |  | 1099 | 0.0048 |  |  | Fully Paid 1099
Furniture | [8 empty] | 0 | After choosing the furniture. |  |  | 0
Papier peint/טפטים | [7 empty] | 3500 | 4130 |  |  |  | 4130
Basement shelves | [7 empty] | 2500 | 2950 |  | 100% | 2950 | 0 |  |  | Fully Paid 2950
TOTAL | [7 empty] | 1459327.151 | 1811363.47 |  |  | 1518827.727 | 127936.5937

## Sheet3
PRIX AVANT TVA | PRIX TTC
15660 | 18478.8
4698 | 5543.64
13780.8
12935.16